## Project Plan
[module title] | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Task Name | Duration | Start - Monday | Finish - Friday | Resource LDS | Resource Walbrook | % Complete | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12
|  | 2025-09-15 |  |  |  | 0%
Kick off meeting | 5 days | 2025-09-15 | 2025-09-19 |  |  | 0%
Initiation meeting held | 5 days | 2025-09-15 | 2025-09-19 | Learning Designer | SME | 0%
Kick off meeting held | 5 days | 2025-09-15 | 2025-09-19 | Learning Designer | SME | 0%
Module Planning Document | 10 days | 2025-09-22 | 2025-10-03 |  |  | 0%
MPD Draft | 5 days | 2025-09-22 | 2025-09-26 | Learning Designer | SME | 0%
MPD Finalised | 5 days | 2025-09-29 | 2025-10-03 | Learning Designer | SME | 0%
Assessment briefs drafted and passed to Programme Leader | 5 days | 2025-09-29 | 2025-10-03 | Learning Designer | SME, Programme Leader | 0%
Reading list revised (if required) | 5 days | 2025-09-29 | 2025-10-03 | Learning Designer | SME, Librarian | 0%
MPD review | 5 days | 2025-10-06 | 2025-10-11 |  | Academic Reviewer | 0% | bar: 2025-10-06
Week 1 | 10 days | 2025-10-06 | 2025-10-17 |  |  | 0%
Week 1 - Storyboard Initial LD Draft | 5 days | 2025-10-06 | 2025-10-10 | Learning Designer |  | 0%
Week 1 - Storyboard SME Scripts Draft | 5 days | 2025-10-06 | 2025-10-10 |  | SME | 0%
Week 1 - Edit | 3 days | 2025-10-13 | 2025-10-15 | Learning Designer | SME | 0%
Week 1 - Storyboard Final draft agreed | 2 days | 2025-10-16 | 2025-10-17 | Learning Designer | SME | 0%
Week 1 - Build | 5 days | 2025-10-20 | 2025-10-25 | Learning Technologist |  | 0%
Week 2 | 5 days | 2025-10-20 | 2025-10-24 |  |  | 0%
Week 2 - Storyboard Initial LD Draft | 2 days | 2025-10-20 | 2025-10-21 | Learning Designer |  | 0%
Week 2 - Storyboard SME Scripts Draft | 2 days | 2025-10-20 | 2025-10-21 |  | SME | 0%
Week 2 - Edit | 2 days | 2025-10-22 | 2025-10-23 | Learning Designer | SME | 0%
Week 2 - Storyboard Final draft agreed | 1 days | 2025-10-24 | 2025-10-24 | Learning Designer | SME | 0%
Week 2 - Build | 5 days | 2025-10-27 | 2025-11-01 | Learning Technologist |  | 0% | bar: 2025-10-27
Week 1 and 2 review | 5 days | 2025-11-03 | 2025-11-08 |  | Academic Reviewer | 0% | bar: 2025-11-03
Week 3 | 5 days | 2025-10-27 | 2025-10-31 |  |  | 0%
Week 3 - Storyboard Initial LD Draft | 2 days | 2025-10-27 | 2025-10-28 | Learning Designer |  | 0%
Week 3 - Storyboard SME Scripts Draft | 2 days | 2025-10-27 | 2025-10-28 |  | SME | 0%
Week 3 - Edit | 2 days | 2025-10-29 | 2025-10-30 | Learning Designer | SME | 0%
Week 3 - Storyboard Final draft agreed | 1 days | 2025-10-31 | 2025-10-31 | Learning Designer | SME | 0%
Week 3 - Build | 5 days | 2025-11-03 | 2025-11-08 | Learning Technologist |  | 0% | bar: 2025-11-03
Week 4 | 5 days | 2025-11-03 | 2025-11-07 |  |  | 0%
Week 4 - Storyboard Initial LD Draft | 2 days | 2025-11-03 | 2025-11-04 | Learning Designer |  | 0%
Week 4 - Storyboard SME Scripts Draft | 2 days | 2025-11-03 | 2025-11-04 |  | SME | 0%
Week 4 - Edit | 2 days | 2025-11-05 | 2025-11-06 | Learning Designer | SME | 0%
Week 4 - Storyboard Final draft agreed | 1 days | 2025-11-07 | 2025-11-07 | Learning Designer | SME | 0%
Week 4 - Build | 5 days | 2025-11-10 | 2025-11-15 | Learning Technologist |  | 0% | bar: 2025-11-10
Film shoot - first batch | 6 days | 2025-11-10 | 2025-11-15 |  | Digital Learning Team | 0% | bar: 2025-11-10
Week 5 | 5 days | 2025-11-10 | 2025-11-14 |  |  | 0%
Week 5 - Storyboard Initial LD Draft | 2 days | 2025-11-10 | 2025-11-11 | Learning Designer |  | 0%
Week 5 - Storyboard SME Scripts Draft | 2 days | 2025-11-10 | 2025-11-11 |  | SME | 0%
Week 5 - Edit | 2 days | 2025-11-12 | 2025-11-13 | Learning Designer | SME | 0%
Week 5 - Storyboard Final draft agreed | 1 days | 2025-11-14 | 2025-11-14 | Learning Designer | SME | 0%
Week 5 - Build | 5 days | 2025-11-17 | 2025-11-22 | Learning Technologist |  | 0% | bar: 2025-11-17
Week 6 | 5 days | 2025-11-17 | 2025-11-21 |  |  | 0%
Week 6 - Storyboard Initial LD Draft | 2 days | 2025-11-17 | 2025-11-18 | Learning Designer |  | 0%
Week 6 - Storyboard SME Scripts Draft | 2 days | 2025-11-17 | 2025-11-18 |  | SME | 0%
Week 6 - Edit | 2 days | 2025-11-19 | 2025-11-20 | Learning Designer | SME | 0%
Week 6 - Storyboard Final draft agreed | 1 days | 2025-11-21 | 2025-11-21 | Learning Designer | SME | 0%
Week 6 - Build | 5 days | 2025-11-24 | 2025-11-29 | Learning Technologist |  | 0% | bar: 2025-11-24
Week 7 | 5 days | 2025-11-24 | 2025-11-28 |  |  | 0%
Week 7 - Storyboard Initial LD Draft | 2 days | 2025-11-24 | 2025-11-25 | Learning Designer |  | 0%
Week 7 - Storyboard SME Scripts Draft | 2 days | 2025-11-24 | 2025-11-25 |  | SME | 0%
Week 7 - Edit | 2 days | 2025-11-26 | 2025-11-27 | Learning Designer | SME | 0%
Week 7 - Storyboard Final draft agreed | 1 days | 2025-11-28 | 2025-11-28 | Learning Designer | SME | 0%
Week 7 - Build | 5 days | 2025-12-01 | 2025-12-06 | Learning Technologist |  | 0% | bar: 2025-12-01
Week 8 | 5 days | 2025-12-01 | 2025-12-05 |  |  | 0%
Week 8 - Storyboard Initial LD Draft | 2 days | 2025-12-01 | 2025-12-02 | Learning Designer |  | 0%
Week 8 - Storyboard SME Scripts Draft | 2 days | 2025-12-01 | 2025-12-02 |  | SME | 0%
Week 8 - Edit | 2 days | 2025-12-03 | 2025-12-04 | Learning Designer | SME | 0%
Week 8 - Storyboard Final draft agreed | 1 days | 2025-12-05 | 2025-12-05 | Learning Designer | SME | 0%
Week 8 - Build | 5 days | 2025-12-08 | 2025-12-13 | Learning Technologist |  | 0% | bar: 2025-12-08
Finalisation | 20 days | 2025-12-08 | 2026-01-02 |  |  | 0%
Film shoot - second batch | 5 days | 2025-12-08 | 2025-12-12 |  | Digital Learning Team | 0%
Proofreading | 5 days | 2025-12-15 | 2025-12-19 |  | Editorial Team | 0%
Weeks 3 to 8 review | 5 days | 2025-12-22 | 2025-12-26 |  | Academic Reviewer | 0% | bar: 2025-12-22
Corrections | 5 days | 2025-12-29 | 2026-01-02 | Learning Designer/ Technologist | SME | 0%
Ready for launch | 1 day | 2026-01-05 |  |  |  | 0% | bar: 2026-01-05
Go live |  | Mon 03/11/25
Note on C5: Microsoft Office User: Manual entry Monday of dev kick off
Note on G5: Microsoft Office User: These are all manually updated
Note on C71: Microsoft Office User: Manual entry launch date

## Roles and notes
[module title]
SME | [name]
Learning Designer | [name]
Learning Technologist | [name]
Programme Manager (PM) | [name]